## Sheet1
Leverett Trails Committee
7:30 p.m. March 20, 2017 Town Hall, 9 Montague Rd, Leverett, MA 01054
Members Present: | Rocky Adriance, Danielle Barshak, Miho Connolly, Neal Erickson, Joan Godsey, David Litterer, Sarah Marcus, Adam Wellen
| Status | Plans | Person(s) Responsible | Notes
STATUS OF TRAILS
Bill Rivers | 1. Railing needs to be installed on second bridge. 2. Old metal bridges need to be removed from the property. 3. Some logs and overhung snags that could be removed. 4. More bog bridges could be installed by stone structures. 5. More signage would be useful on the red trail. | Railings will be installed on our next workday. The Transfer Station expressed an interest in the metal bridges, but we have not heard back yet. | Miho will continue to reach out to the Hwy Dept about the metal bridges. WORK DAY 3/25@8:30AM to install railings. [EDIT: CANCELLED]
4H Forest | Neal's trail needs more benching, and signage by the powerlines. | We want to figure out a way to access the island and install a bench. A chainsaw is needed to cut a log at entrance. Some trail markers may need to be revised. Vista pruning of dead branches? | BRAINSTORM ways to get to the island. WORKDAY 5/13 @ 8:30AM
Gordon King |  | We will prune the blueberry bushes and burn the brushpile in advance of the Gordon King dedication event. | WORKDAY 4/1 @ 8:30AM. [EDIT: RESCHEDULED TO 4/8]
Ed Field Trail | We can nail green trail tags to the white posts on the Vernal Pool trail so that it is easier to follow. | The current color for the trail is orange-- this should be changed to green so that the marking is consistent. | Miho?
Teawaddle Hill Farm | There is interest in creating trails in the western area of the property. | Gwyn and Bill have no problem with the creation of new trails. We should consider putting in RTV accessible trails here.
Cave Hill | Area of blue trail traverses wet patch that could easily be avoided by changing the trail. A bog bridge would be useful at the stream crossing on the Town Farm Loop. | Change route of blue trail to avoid wet spot. Install additional bog bridge on Town Farm Loop. Boundary Rocks trail is hazardous and should be closed. Fix typo ("you data"). | Later workday?
Ruth MacIntyre | We should put in a trail that connects the parking lot to the Robert Frost trail. The GPS tracks of the RF trail on the trail maps need revising.
OTHER BUSINESS
Eversource "Rte 66" | Members expressed discontent at the creation of thoroughfares in the Eversource right-of-ways | Is it possible to stop National Grid from undertaking a similar project? | Miho will discuss the issue with DEP | The roads are required by state? feds? to ensure faster repairs in storms.
The Kings of Leverett Library Exhibit | The April library exhibit will celebrate the lives of Gordon and Frances King. The opening event at 1:00PM on April 1 [RESCHEDULED: April 22] will include photographs, videos, and stories about the pair. There will be a dedication event at 3:30PM [RESCHEDULED: April 8 @ 11:30AM] at the Gordon King Life Estate. | LTC supports the exhibit. We will hold a work day at the Gordon King Life Estate before the opening event. | Co-sponsored by Rattlesnake Gutter Trust, Leverett Trails Committee, Leverett Historical Society, and Conservation Commission.
LES Leverett Trails Appreciation Day | Sarah Marcus contacted the LTC about coordinating a trails appreciation event in the Bill Rivers CA behind LES. Tentatively scheduled for Sat. 6/3, 10AM-1PM. In collaboration with Wolftree Programs, LES PTO, and LTC. | We need to discuss with Sarah on how to proceed. We could fell some trees to create a vista at the top of the hill, where a bench could also be placed. The orange trail could still use some rerouting to avoid/mitigate the path through the steep rock field. We can start work on the green trail soon. |  | Students could name the trail or hill? Keep a notebook of wildlife sightings? Could a bonfire or food be part of the event?
Community Preservation Act Grant | The CPC will be voting on April 5 on whether or not to pass projects to Town meeting
Leverett Community Trail | A small group met on March 9 to discuss how to implement an accessible trail with fitness structures near the LES. | The group is planning to apply for next year's DCR Recreational Trails Grant.
Cave Hill Geology & Nature Walk April 29 | Nancy Goodman and Richard Little are leading a walk at Cave Hill through PVI & GCC. They are expecting ~35 cars. | Participants will be allowed to park at the Peace Pagoda.
Biothon? | The Hitchcock Center is holding a biothon fundraiser on Mt Toby on April 3. | Perhaps we can do a biothon in Leverett? (Potentially as past of the Trails Appreciation Day?)
DATES
| Saturday, Feb 11 8:30AM - 12:30PM (Rain date: Saturday, Feb 25) | Bill Rivers CA: Reconnaissance/bushwhacking to map out a new trail for students to work on at the proposed LES "hike-a-thon" | Attendees limited to those at meeting and those invited by word of mouth.
WORK DAYS | Saturday, March 25 8:30AM - 12:30PM [EDIT: CANCELLED] | Bill Rivers CA: Construction of railings on existing bridges. Removal of fallen logs (chainsaws)?
| Saturday, April 1 8:30AM - 12:30PM [EDIT: RESCHEDULED TO APRIL 8] | Gordon King Life Estate: Pruning, clean-up, brush burning.
OTHER EVENTS IN TOWN
NEXT MEETING: | 7:30p.m. April 17, 2017