## Prioritization Plan
Complete Streets Funding Program
Project Prioritization Plan
Municipality |  | Leverett |  | Public Engagement
MassDOT District |  | 2 |  | Public Engagement Description
Name |  | Marjorie McGinnis |  | A public input meeting was held on Jan. 30, 2025 that was attended by 19 communiyt members. Info about the Plan was shared in a Story Map that was posted on the Town website. Mulltiple public comments wre received via email. The plan was presented at a Town Select Board meeting on Feb. 25, 2025 and approved for submission by the Select Board on March 11, 2025..
Title |  | Town Administrator
Date |  | 2025-03-13
Project Basics |  |  |  | Location |  | Modes Served |  |  |  | Project Types | [26 empty] | Assessment | [8 empty] | Funding Request |  |  | Construction Schedule
Project Priority Ranking | Project Name | Project Description | Project Source | Project Location | Google Maps Link | Pedestrian | Bicycle | Transit | Vehicle/Freight | Intersection Redesign |  |  |  | Street Reconfigurations & Traffic Calming |  |  | Pedestrian Crossing Modifications | [6 empty] | Pedestrian & Bike Network Connections |  |  |  |  | Transit Investments |  | Environment & Streetscape Investments | [5 empty] | Network Gap | High Crash Location |  |  | Environmental Justice | Safe Routes to School | Safe Routes for Seniors | Accessibility | State-owned ROW
[10 empty] | Roundabouts/Mini Traffic Circle | Intersection Reconstruction | Tighten Curb Radii/Curb Extension | Intersection Signalization | Road Diet/Lane Elimination | Lane Narrowing | Other Traffic Calming Elements | ADA-compliant Curb Ramps | Pedestrian Hybrid Beacon/HAWK | Ped-Activated Warning Device/RRFBs | Pedestrian Signal Upgrades | Crossing Islands | Raised Intersection or Raised Crosswalk | Crosswalk Improvements | Sidewalk | Shared-Use Path/Separated Bike Lane | On-road Bike Lane | Bicycle Boulevards | At-grade Rail Crossing Improvements | Transit Station/Stop Access Improvements | Transit Service Improvements | Street Lighting | Wayfinding for Pedestrians/Bicyclists | Bicycle Parking | Bicycle-Friendly Drain Grates | Stormwater Management | Street Trees/Landscaping | Is a Network Gap being filled? | Pedestrian | Bicycle | Vehicle | Is an Environmental Justice Population Served? (See MassGIS Map) | Does this project improve safety or accessibility within one mile of a school? | Does this project improve safety or accessibility within 1/4 mile of a Senior destination? | Does this project improve conditions for people with disabilities? | Does this project include any state-owned right-of-way? | Estimated Project Cost Range | Funding Requested from MassDOT | Other Funding Source(s) & Amount (if applicable) | Anticipated Construction Duration
1 | Pedestrian Crossing Improvements at the Town Hall/Post Office/Church Montague Road and Putney Road | Establish an ADA-compliant raised pedestrian crosswalk with Rectangular Rapid Flashing Beacons (RRFBs) on Montague Road at Putney Road. Include MUTCD-compliant warning signs. | CS Needs Assessment | 9 Montague Road. Intersection of Montague Road and Putney Road | https://maps.app.goo.gl/jooLq1iVo2m6j64QA | Yes | No | No | No | No | No | No | No | No | No | Yes | Yes | No | Yes | Yes | No | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes | No | $50,000 - $100,000 | 70000 |  | 1
2 | Crossing Improvements in North Leverett Historic District | Construct an ADA-compliant raised crosswalk and curb ramps on North Leverett Road at Cave Hill Road (between Church & Pavilion) and an ADA-compliant crosswalk and curb ramps at grade on Cave Hill Road at North Leverett Road. Include Rectangular Rapid Flashing Beacons (RRFBs) at the crossing on North Leverett Road and MUTCD-compliant warning signs as warranted | CS Needs Assessment | North Leverett Road and Cave Hill Road | https://maps.app.goo.gl/GQtRuFBajXwJKsQF7 | Yes | No | No | Yes | No | No | No | No | No | No | Yes | Yes | No | Yes | No | No | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | $50,000 - $100,000 | 85000 |  | 1
3 | Pedestrian and Bicycle Connection from Town Hall to Public Library | Construct a shared-use path, approx. 3,250 ft long, on the eastern side of Montague Road from the Town Hall to the Public Library | CS Needs Assessment | from #9 Montague Road to #75 Montague Road | https://maps.app.goo.gl/THbkr8zmmFMnFn9p8 | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | Yes | Yes | Yes | No | >$500,000 | 500000 | $50,000 Ch. 90, grants | 3
4 | Bicycle Accommodations along North Leverett Road from the Leverett Village Co-Op to Town Line | Increase awareness of bicyclists by installing Franklin County Bikeway signs and speed feedback signs in both directions to caution drivers, improving safety for cyclists on this narrow, winding road. | CS Needs Assessment | North Leverett Road from Moore's corner intersection ( Dudleyville Road, Rattlesnake Gutter Road, North Leverett Road and Church Hill Road) to Shutesbury Town Line | https://maps.app.goo.gl/Z8YmJyKsKWg8AavP9 | Yes | Yes | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | Yes | No | <$50,000 | 50000 |  | 1
5 | School Bus Stop Accommodations | Improve access to school bus stops on local roads, by clearing roadside vegetation, constructing permeable walking surface away from the edge of pavement, and providing a safe waiting area away from the road shoulder | CS Needs Assessment | Bull Hill Road at Route 63, Depot Road at Route 63, others to be identified | https://maps.app.goo.gl/jCntH52i4T7fUdT9A | Yes | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | $100,000 - $250,000 | 110000 |  | 2
6 | Intersection Improvements at Depot Road/Shutesbury Road /Montague Road | Improve pedestrian and bicyclist safety at the confusing Y-intersection of Depot, Shutesbury, and Montague Roads by enhancing wayfinding signage and revising pavement marking and signage to ensure visibility and MUTCD-compliance. | CS Needs Assessment | Depot Road/Shutesbury Road/Montague Road Intersection | https://maps.app.goo.gl/P7m3DLue93wjyCGy5 | Yes | Yes | No | Yes | No | No | No | Yes | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes | No | <$50,000 | 45000 |  | 1
7 | Parking and Crossing Improvements at the Town Pond on Depot Road | Construct a wheelchair-accessible parking spot on the north side (pond side) of Depot Rd. Create an ADA-compliant raised crosswalk with RRFB. Formalize the parking spots on the south side of Depot Rd with surface improvements and signage. Install a bike rack at the Pond | CS Needs Assessment | Between 137 Depot Road and 1 Shutesbury Road | https://maps.app.goo.gl/N3FAL1LHvz6yiSALA | Yes | Yes | No | Yes | No | No | No | No | No | No | Yes | Yes | No | Yes | Yes | No | Yes | Yes | No | No | No | No | No | No | No | No | Yes | Yes | No | No | No | No | No | No | No | No | Yes | Yes | Yes | No | $50,000 - $100,000 | 95000 |  | 1
8 | Pedestrian and Bicycle Connection from Town Pond to Town Hall | Construct a shared-use path, approx. 675 ft long, connecting the Town Pond Boat Ramp on Depot Road to Leverett Town Hall on Montague Road. | CS Needs Assessment | Between 137 Depot Road and 9 Montague Road | https://maps.app.goo.gl/GYHEYDWzWT5oFfRbA | Yes | Yes | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | Yes | Yes | No | Yes | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | Yes | Yes | Yes | No | $50,000 - $100,000 | 90000 |  | 2
9 | Intersection Reconstruction Chestnut Hill Road at North Leverett Road | Reconstruct the intersection of Chestnut Hill Rd at N Leverett Rd from a "Y" to a "T" to reduce confusion for all users, improve sight distance, and to provide shorter crossing distance for pedestrians. Include MUTCD-compliant STOP sign and ADA-compliant crosswalk & curb ramps | CS Needs Assessment | Chestnut Hill Road at North Leverett Road | https://maps.app.goo.gl/kjT8d9vNbARREHgH9 | Yes | Yes | No | Yes | No | Yes | Yes | No | No | Yes | No | Yes | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | >$500,000 | 500000 | $500,000 Ch. 90, TIP, grant | 3
10 | Intersection Reconstruction in Moore’s Corner Historic District | Improve safety and accessibility at the five-way intersection near the Leverett Co-Op by eliminating slip lanes, creating T-intersections for Church Hill, Dudleyville, and Rattlesnake Gutter Roads. Raze vacant buildings and clear site; designate a parking area for hikers. Include ADA-compliant crosswalks with curb ramps at intersecting streets and MUTCD-compliant signs as warranted. | CS Needs Assessment | Intersection of Dudleyville Road, Rattlesnake Gutter Road, North Leverett Road and Church Hill Road | https://maps.app.goo.gl/UvgTdygcjhn182TD8 | Yes | Yes | No | Yes | No | Yes | No | No | No | No | Yes | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | Yes | Yes | No | No | No | No | No | No | No | No | No | No | Yes | No | >$500,000 | 500000 | $1,000,000 TIP, grant | 4
11 | Pedestrian and Bicycle Connection on Montague Road from Elementary School to Cave Hill Road | Construct a shared-use path, approx. 5280 ft long, on the eastern side of Montague Road from the Elementary School to Cave Hill Road | CS Needs Assessment | Montague Road from Cave Hill Road south to 85 Montague Road (Leverett Elementary School) | https://maps.app.goo.gl/EUMuvCZK4oVJZYx88 | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | Yes | Yes | Yes | No | >$500,000 | 500000 | $200,000 Ch. 90, TIP | 3
12 | Bus Stop Improvements at the Post Office on Montague Road | Relocate bus stop to the First Congregational Church parking area, separating it from Post Office parking, and construct a bus shelter with bench & bike rack. Include pavement markings to delineate bus parking area from church entrance & adjacent Putney Road | CS Needs Assessment | Parking lot of First Congregational Church of Leverett on 4 Montague Road | https://maps.app.goo.gl/9MGGJf86h9X1pZ6E9 | Yes | Yes | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | Yes | No | No | No | No | No | No | No | No | Yes | Yes | Yes | No | <$50,000 | 45000 |  | 1
13 | Town Wide Traffic Calming | Reduce vehicle speeds on major town roads using a variety of interventions, including Speed Feedback Signs, speed humps, rumble strips, and edge and centerline pavement markings. | CS Needs Assessment | Amherst Road, Cave Hill Road, Cushman Road, Depot Road, Montague Road, North Leverett Road, Shutesbury Road | https://maps.app.goo.gl/fVdQDgxD5SpjnGVW6 | Yes | Yes | No | Yes | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | No | Yes | Yes | Yes | No | >$500,000 | 500000 | $100,000 Ch. 90, TIP, grants | 2
14 | Pedestrian and Bicycle Connection in North Leverett Historic District | Construct a shared-use path, approx. 4,400 ft long, on one side of North Leverett Road from West Chestnut Hill Rd to approx. 102 N. Leverett Rd. Include ADA-compliant crosswalks and curb ramps at side streets. | CS Needs Assessment | North Leverett Road from West Chestnut Hill Rd to approx. 102 N. Leverett Road | https://maps.app.goo.gl/vJgZqZqtfgMeoW2S7 | Yes | Yes | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | Yes | No | Yes | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | Yes | No | >$500,000 | 500000 | $1,500,000 TIP | 4
15 | Bicycle and Pedestrian Accommodation Improvements at Shutesbury Road and Cushman Road | Enhance safety by improving signage, adding street lighting, and installing ADA-compliant crosswalks with curb ramps and MUTCD-compliant warning signs at the Shutesbury and Cushman Road intersection. | CS Needs Assessment | Intersection of Cushman Road and Shutesbury Road | https://maps.app.goo.gl/9LZzCeLjcQMH9jLC6 | Yes | Yes | No | Yes | No | No | No | No | No | No | Yes | Yes | No | No | Yes | No | Yes | Yes | No | No | No | No | No | No | No | Yes | Yes | No | No | No | No | No | No | No | No | No | No | No | Yes | No | $50,000 - $100,000 | 87500 |  | 1
16 | Pedestrian Crossing Improvements at Roaring Brook Conservation Area Trailhead (Former M&M Trail) | Improve pedestrian visibility and safety at the hiking trail crossing on Shutesbury Road by adding MUTCD-compliant signage, creating an ADA-compliant raised crosswalk, and installing Rectangular Rapid Flashing Beacons (RRFBs) to alert drivers. | CS Needs Assessment | Trailhead parking southwest of Old Mountain Road and Shutesbury Road intersection | https://maps.app.goo.gl/SaYomyKtRcotVK6X9 | Yes | No | No | Yes | No | No | No | No | No | No | Yes | Yes | No | Yes | No | No | Yes | Yes | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | No | No | No | No | No | No | Yes | No | $50,000 - $100,000 | 85000 |  | 1
17 | Separated Shared Use Paths along Bike Routes | Construct separated or off-road paths along desirable biking routes in town, including Cave Hill Road and roads along the Franklin County Bikeway. Include ADA-compliant crosswalks and curb ramps at all street crossings; path lighting where necessary. | CS Needs Assessment | Amherst Road, Cave Hill Road, Montague Road, North Leverett Road, Shutesbury Road | https://maps.app.goo.gl/fVdQDgxD5SpjnGVW6 | Yes | Yes | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | No | Yes | No | Yes | No | No | No | No | No | No | Yes | No | No | No | No | Yes | No | No | No | No | No | No | Yes | No | >$500,000 | 500000 | $13,500,000 TIP, grants | 12
18 | Pedestrian & Bicycle Connection on Montague Road from Leverett Public Library to Leverett Elementary School | Construct a shared-use path, approx. 500 ft long, along the eastern side of Montague Road (between the stonewall and treeline), connecting the Leverett Town Library to the Leverett Elementary School and nearby amenities. | ADA Transition Plan/Assessment | Eastern side of Montague Road from Library to Elementary School | https://maps.app.goo.gl/Se2ZGwcuBDrfdeJk9 | Yes | Yes | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | Yes | Yes | No | Yes | No | No | No | No | No | No | No | No | No | No | No | Yes | No | No | No | No | Yes | Yes | Yes | No | $50,000 - $100,000 | 75000 |  | 2
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Eligible Projects
Eligible Complete Street Project Types
If a project type or element does not appear in this list, it may still be eligible for funding. The applicant should provide justification for the decision based upon the classification of comparable projects. Include justification in the project description. Check the Ineligible Project list to ensure the project type or element is not excluded from funding.
Intersection Redesign | Street Reconfigurations & Traffic Calming | Pedestrian Crossing Modifications | Pedestrian & Bike Network Connections | Transit Investments | Environment & Streetscape Investments
Projects that address infrastructure barriers to walking, biking, or taking transit at a signalized or unsignalized intersection including spot improvements such as tightening curb radii, adding curb extensions, adding a roundabout or mini traffic circle, adding bicycle facilities, and/or reducing vehicular speeds. | Projects that reallocate roadway space from vehicles to provide exclusive space for people walking, biking, and/or taking transit. | Projects that enhance pedestrian crossings at a signalized, unsignalized, or midblock crossing by upgrading curb ramps and/or adding RRBFs, crossing islands, raised intersections or crosswalks, markings, and/or signs. | Projects that add new pedestrian and/or bike facilities along a roadway segment such as sidewalks, shared use paths, separated bike lanes, or bike lanes. | Projects that enhance transit access through station and stop improvements and/or service improvements such as bus lanes, queue jumps, or transit signal priority. | Projects that incorporate streetscape amenities such as street lighting, wayfinding, bicycle parking, stormwater management, and/or street trees and landscaping.
Roundabouts/Mini Traffic Circle | Road Diet/Lane Elimination | ADA-compliant Curb Ramps | Sidewalk | Transit Station/Stop Access Improvements (curb ramps, bus shelters, bike parking, Park & Ride, etc.) | Street Lighting
Intersection Reconstruction (addresses multimodal issues) | Lane Narrowing (adds exclusive bike space) | Pedestrian Hybrid Beacon/HAWK | Shared-Use Path/Trail | Transit Service Improvements (bus lanes, bus pullouts, TSP, etc.) | Wayfinding for Pedestrians/Bicyclists
Tighten Curb Radii/Curb Extension (at pedestrian crossing) | Other Traffic Calming Elements | Pedestrian-Activated Warning Device/Rectangular Rapid Flashing Beacons (RRFB) | On-road Bike Lane* |  | Bicycle Parking
Intersection Signalization (addresses multimodal issues) |  | Pedestrian Signal Upgrades | Bicycle Boulevards |  | Bicycle-Friendly Drain Grates
|  | Crossing Islands | At-grade Rail Crossing Improvements (for people biking) |  | Stormwater Management
|  | Raised Intersection or Raised Crosswalk | Separated Bike Lane |  | Street Trees/Landscaping
Crosswalk Improvements
*Resurfacing is not an eligible item unless a designated bike facility is being added

## Ineligible Projects
Ineligible Complete Street Project Types
The following project types are NOT eligible for Complete Streets Funding Program funding:
Ineligible Project Types | Notes
All projects on facilities where bicyclists and pedestrians are prohibited | Example: Freeways posted to exclude non-motorized transportation.
State-owned roadways
Projects done under Minor Vehicle Access Permit or Non-Vehicle Access Permits
Routine roadway maintenance projects | Example: Pothole patching, crack sealing, joint repair, micro surfacing, chip seals, etc.
Non-roadway maintenance projects | Example: Catch basin cleaning, street sweeping, grass mowing, etc.
Bridge maintenance projects | Example: Joint repair, deck repair, superstructure repair, substructure repair, etc.
Emergency repairs
Drainage-only projects
Guardrail-only projects
Landscape-only projects
Signage-only projects | Bike wayfinding/bike route signing eligible.
Noise barrier-only projects
Shim/leveling projects
Vertical construction | Covered bicycle parking shelters and covered bus shelters eligible.
Pedestrian bridges

## Instructions
Complete Streets Funding Program
Project Prioritization Plan Instructions
| General Information | Description | Additional Resources
| Municipality | Select your City or Town name from the drop-down list
| MassDOT District | MassDOT District the municipality belongs to (this field will auto-fill) | MassDOT Districts
| Name | Input name of person filling out the form
| Title | Input title of person filling out the form
| Date | Input date form is completed (MM-DD-YYYY)
| Public Engagement | Description | Additional Resources
| Public Engagement Description | Write a brief description (2-5 sentences) of the public engagement process and any metrics collected demonstrating its effectiveness or reach.
| Project Information | Description | Additional Resources
Project Basics | Project Priority Ranking | Rank projects based on the results of your local prioritization process, from highest to lowest priority.
| Project Name | Enter name of the project. It is helpful to include street name(s) and improvement type to track various projects and improvement type over time.
| Project Description | Write a brief description (1-3 sentences) of the project components and what it intends to accomplish.
| Project Source | Identify the analysis or planning document that identified the complete street project need. Select the type/origin of the Complete Streets project from the drop-down list. Choose one of the following: • Capital Improvement Program (CIP) • CS Needs Assessment Private Development Review • Roadway Maintenance Plan • ADA Transition Plan/Assessment • Safety/Pedestrian/Bicycle Audit • Master Plan • Scheduled Utility Work • Other
Location | Project Location | Add any additional location details you deem necessary, such as project extends, major intersections, etc.
| Google Maps Link | Provide a Google Maps link to the general location of your project | www.google.com/maps
Modes Served | Pedestrian | Indicate what modes the project will serve and improve. Indicate "Yes" if that mode is served and "No" if it is not served. Include all modes the project will address. NOTE: The most competitive projects provide improvements for at least two (2) modes.
Bicycle
Transit
Vehicles/Freight
Project Types | Intersection Redesign | Each Project Category includes a number of Project Types eligible for funding under the Complete Streets Funding Program. Select "Yes" under any project type that your project includes . There is no minimum or maximum number of number of project types that you can select. For a full list of eligible projects, see the "Eligible Projects" tab in this document. | Eligible Projects List
| Street Reconfigurations & Traffic Calming |  | Ineligible Projects List
Pedestrian Crossing Modifications
Pedestrian & Bike Network Connections
Transit Investments
Environment & Streetscape Investments
Assessment | Network Gap | Indicate if this project provides an important connection or fills a network gap. For example, the proposed new sidewalk segment connects two existing sidewalks or the bike lane continues an existing bike lane.
| High Crash Location | Indicate if this project is located in a pedestrian, bicycle, and/or vehicle High Crash location. High crash locations are defined by MassDOT’s Highway Safety Improvement Program (HSIP) crash data, local police data or from the Regional Planning designation. | https://gis.massdot.state.ma.us/topcrashlocations/
| Environmental Justice | Using the MassGIS Mapping Tool, determine if the project is within or serves a designated Environmental Justice population. | http://maps.massgis.state.ma.us/map_ol/ej.php
| Safe Routes to School | Indicate if this project improves safety or accessibility to a school (K-12 and/or college), improves safety leading to a school, or is located on an important route to school. Project must be within 1 mile of the school.
| Safe Routes for Seniors | Indicate if this project improves safety or accessibility to a Senior Center and/or Independent Living Facility or an important route for seniors to access community destinations. Project must be within 1/4 mile of the senior facility.
| Accessibility | Indicate if this project improves conditions for people with disabilities.
| State-owned ROW | Indicate if any part of your project includes MassDOT owned right-of-way (ROW).
Estimated Project Cost | Total Project Cost | Input total costs for the project, including as applicable, ROW, utilities, design, construction. Use only whole dollar amounts.
| Complete Streets Funding Requested | Input amount of construction funding requested from Complete Streets program (up to 100% of total construction cost). Funding can range up to $500,000 for each municipality.
| Other Funding Source(s) (if applicable) | If your project exceeds $500,000 in estimate costs, please list other funding sources outside of the Complete Streets Funding Program and estimated amounts that will cover these additional costs. e.g. Chapter 90, $30,000; Safe Routes to School, $80,000.
Construction Schedule | Anticipated Construction Duration | Provide an estimated number of months required from start to end of construction. Use whole numbers (e.g. 5).

## DropDowns (hidden)
Complete Streets Project Origin
Capital Improvement Program (CIP)
CS Needs Assessment
Private Development Review
Roadway Maintenance Plan
ADA Transition Plan/Assessment
Safety/Pedestrian/Bicycle Audit
Master Plan
Scheduled Utility Work
Other
Complete Streets Project Type
Intersection Redesign
Street Reconfigurations & Traffic Calming
Pedestrian Crossing Modifications
Pedestrian & Bike Network Connections
Transit Investments
Environment & Streetscape Investments
Yes
No
X
Funding
<$50,000
$50,000 - $100,000
$100,000 - $250,000
$250,000 - $500,000
>$500,000

## Muni Info (hidden)
Municipality | Median Household Income | Below Statewide Average? | District
SELECT | 0 |  | --
Abington | 81500 | NO | 5
Acton | 120865 | NO | 3
Acushnet | 69570 | NO | 5
Adams | 41807 | YES | 1
Agawam | 63561 | YES | 2
Alford | 91250 | NO | 1
Amesbury | 76463 | NO | 4
Amherst | 52537 | YES | 2
Andover | 125321 | NO | 4
Aquinnah | 65833 | YES | 5
Arlington | 92338 | NO | 4
Ashburnham | 85662 | NO | 3
Ashby | 83917 | NO | 3
Ashfield | 71364 | NO | 1
Ashland | 102721 | NO | 3
Athol | 47122 | YES | 2
Attleboro | 65141 | YES | 5
Auburn | 72695 | NO | 3
Avon | 78750 | NO | 5
Ayer | 67110 | YES | 3
Barnstable | 58933 | YES | 5
Barre | 66250 | YES | 2
Becket | 64152 | YES | 1
Bedford | 114676 | NO | 4
Belchertown | 74221 | NO | 2
Bellingham | 87417 | NO | 3
Belmont | 105859 | NO | 4
Berkley | 84423 | NO | 5
Berlin | 88681 | NO | 3
Bernardston | 59167 | YES | 2
Beverly | 73980 | NO | 4
Billerica | 93761 | NO | 4
Blackstone | 72699 | NO | 3
Blandford | 72361 | NO | 1
Bolton | 144461 | NO | 3
Boston | 54485 | YES | 6
Bourne | 63664 | YES | 5
Boxborough | 103996 | NO | 3
Boxford | 127813 | NO | 4
Boylston | 102422 | NO | 3
Braintree | 87500 | NO | 6
Brewster | 66306 | YES | 5
Bridgewater | 88481 | NO | 5
Brimfield | 82365 | NO | 2
Brockton | 48569 | YES | 5
Brookfield | 63889 | YES | 3
Brookline | 93640 | NO | 6
Buckland | 52356 | YES | 1
Burlington | 95465 | NO | 4
Cambridge | 75909 | NO | 6
Canton | 90878 | NO | 6
Carlisle | 157500 | NO | 4
Carver | 72804 | NO | 5
Charlemont | 49000 | YES | 1
Charlton | 91287 | NO | 3
Chatham | 63299 | YES | 5
Chelmsford | 93643 | NO | 4
Chelsea | 48725 | YES | 6
Cheshire | 54741 | YES | 1
Chester | 65648 | YES | 1
Chesterfield | 63594 | YES | 1
Chicopee | 47276 | YES | 2
Chilmark | 67813 | YES | 5
Clarksburg | 57375 | YES | 1
Clinton | 64867 | YES | 3
Cohasset | 117679 | NO | 5
Colrain | 46452 | YES | 1
Concord | 132385 | NO | 4
Conway | 79286 | NO | 1
Cummington | 50521 | YES | 1
Dalton | 47500 | YES | 1
Danvers | 77404 | NO | 4
Dartmouth | 68684 | NO | 5
Dedham | 85558 | NO | 6
Deerfield | 75307 | NO | 2
Dennis | 50860 | YES | 5
Devens | 67679 | YES | 3
Dighton | 85326 | NO | 5
Douglas | 84616 | NO | 3
Dover | 176250 | NO | 6
Dracut | 76786 | NO | 4
Dudley | 68053 | NO | 3
Dunstable | 116125 | NO | 3
Duxbury | 120253 | NO | 5
East Bridgewater | 88534 | NO | 5
East Brookfield | 71020 | NO | 3
East Longmeadow | 84173 | NO | 2
Eastham | 62452 | YES | 5
Easthampton | 56927 | YES | 2
Easton | 95372 | NO | 5
Edgartown | 56911 | YES | 5
Egremont | 54556 | YES | 1
Erving | 61083 | YES | 2
Essex | 89185 | NO | 4
Everett | 51056 | YES | 4
Fairhaven | 60445 | YES | 5
Fall River | 33763 | YES | 5
Falmouth | 64070 | YES | 5
Fitchburg | 46628 | YES | 3
Florida | 52313 | YES | 1
Foxborough | 94538 | NO | 5
Framingham | 68881 | NO | 3
Franklin | 101980 | NO | 3
Freetown | 87830 | NO | 5
Gardner | 46589 | YES | 3
Georgetown | 106898 | NO | 4
Gill | 75776 | NO | 2
Gloucester | 60229 | YES | 4
Goshen | 69219 | NO | 1
Gosnold | 31406 | YES | 5
Grafton | 81250 | NO | 3
Granby | 78261 | NO | 2
Granville | 75208 | NO | 1
Great Barrington | 52026 | YES | 1
Greenfield | 48493 | YES | 2
Groton | 116686 | NO | 3
Groveland | 92898 | NO | 4
Hadley | 74737 | NO | 2
Halifax | 69917 | NO | 5
Hamilton | 108558 | NO | 4
Hampden | 78722 | NO | 2
Hancock | 80395 | NO | 1
Hanover | 98750 | NO | 5
Hanson | 93771 | NO | 5
Hardwick | 59148 | YES | 2
Harvard | 131563 | NO | 3
Harwich | 67332 | YES | 5
Hatfield | 60033 | YES | 2
Haverhill | 61208 | YES | 4
Hawley | 68000 | NO | 1
Heath | 56458 | YES | 1
Hingham | 103350 | NO | 5
Hinsdale | 63953 | YES | 1
Holbrook | 63297 | YES | 5
Holden | 97972 | NO | 3
Holland | 64868 | YES | 2
Holliston | 108350 | NO | 3
Holyoke | 35550 | YES | 2
Hopedale | 99886 | NO | 3
Hopkinton | 128267 | NO | 3
Hubbardston | 83438 | NO | 3
Hudson | 74082 | NO | 3
Hull | 77440 | NO | 5
Huntington | 52275 | YES | 1
Ipswich | 77901 | NO | 4
Kingston | 86339 | NO | 5
Lakeville | 82418 | NO | 5
Lancaster | 81833 | NO | 3
Lanesborough | 72708 | NO | 1
Lawrence | 34496 | YES | 4
Lee | 59019 | YES | 1
Leicester | 68790 | NO | 3
Lenox | 51201 | YES | 1
Leominster | 59263 | YES | 3
Leverett | 78125 | NO | 2
Lexington | 137456 | NO | 4
Leyden | 74375 | NO | 2
Lincoln | 127763 | NO | 4
Littleton | 111652 | NO | 3
Longmeadow | 108835 | NO | 2
Lowell | 49164 | YES | 4
Ludlow | 61410 | YES | 2
Lunenburg | 71055 | NO | 3
Lynn | 47195 | YES | 4
Lynnfield | 114816 | NO | 4
Malden | 55523 | YES | 4
Manchester-by-the-Sea | 89313 | NO | 4
Mansfield | 93082 | NO | 5
Marblehead | 100709 | NO | 4
Marion | 76607 | NO | 5
Marlborough | 71424 | NO | 3
Marshfield | 89702 | NO | 5
Mashpee | 65768 | YES | 5
Mattapoisett | 78216 | NO | 5
Maynard | 79252 | NO | 3
Medfield | 143641 | NO | 3
Medford | 77868 | NO | 4
Medway | 109841 | NO | 3
Melrose | 86409 | NO | 4
Mendon | 112104 | NO | 3
Merrimac | 80508 | NO | 4
Methuen | 68587 | NO | 4
Middleborough | 75727 | NO | 5
Middlefield | 78214 | NO | 1
Middleton | 105646 | NO | 4
Milford | 68007 | NO | 3
Millbury | 71676 | NO | 3
Millis | 96773 | NO | 3
Millville | 88281 | NO | 3
Milton | 113087 | NO | 6
Monroe | 32083 | YES | 1
Monson | 66389 | YES | 2
Montague | 47236 | YES | 2
Monterey | 48750 | YES | 1
Montgomery | 78333 | NO | 1
Mount Washington | 65417 | YES | 1
Nahant | 65083 | YES | 4
Nantucket | 86529 | NO | 5
Natick | 98902 | NO | 3
Needham | 129154 | NO | 6
New Ashford | 73750 | NO | 1
New Bedford | 36813 | YES | 5
New Braintree | 81136 | NO | 2
New Marlborough | 64559 | YES | 1
New Salem | 78667 | NO | 2
Newbury | 95827 | NO | 4
Newburyport | 83149 | NO | 4
Newton | 118639 | NO | 6
Norfolk | 143682 | NO | 5
North Adams | 37654 | YES | 1
North Andover | 100544 | NO | 4
North Attleborough | 81847 | NO | 5
North Brookfield | 58438 | YES | 3
North Reading | 112419 | NO | 4
Northampton | 58179 | YES | 2
Northborough | 107111 | NO | 3
Northbridge | 70399 | NO | 3
Northfield | 60721 | YES | 2
Norton | 80806 | NO | 5
Norwell | 110671 | NO | 5
Norwood | 79963 | NO | 5
Oak Bluffs | 80225 | NO | 5
Oakham | 80577 | NO | 3
Orange | 41473 | YES | 2
Orleans | 58235 | YES | 5
Otis | 55833 | YES | 1
Oxford | 70016 | NO | 3
Palmer | 51846 | YES | 2
Paxton | 99375 | NO | 3
Peabody | 62234 | YES | 4
Pelham | 88462 | NO | 2
Pembroke | 89954 | NO | 5
Pepperell | 77767 | NO | 3
Peru | 68971 | NO | 1
Petersham | 65625 | YES | 2
Phillipston | 78490 | NO | 2
Pittsfield | 43489 | YES | 1
Plainfield | 57188 | YES | 1
Plainville | 78516 | NO | 5
Plymouth | 76925 | NO | 5
Plympton | 94505 | NO | 5
Princeton | 114688 | NO | 3
Provincetown | 41250 | YES | 5
Quincy | 62710 | YES | 6
Randolph | 63259 | YES | 6
Raynham | 80056 | NO | 5
Reading | 103913 | NO | 4
Rehoboth | 85691 | NO | 5
Revere | 50900 | YES | 4
Richmond | 77396 | NO | 1
Rochester | 94688 | NO | 5
Rockland | 66860 | YES | 5
Rockport | 70288 | NO | 4
Rowe | 54375 | YES | 1
Rowley | 85994 | NO | 4
Royalston | 60568 | YES | 2
Russell | 68750 | NO | 1
Rutland | 91033 | NO | 3
Salem | 59044 | YES | 4
Salisbury | 75995 | NO | 4
Sandisfield | 56250 | YES | 1
Sandwich | 84167 | NO | 5
Saugus | 76141 | NO | 4
Savoy | 57222 | YES | 1
Scituate | 102577 | NO | 5
Seekonk | 74242 | NO | 5
Sharon | 127413 | NO | 5
Sheffield | 50530 | YES | 1
Shelburne | 54167 | YES | 1
Sherborn | 155564 | NO | 3
Shirley | 66453 | YES | 3
Shrewsbury | 97365 | NO | 3
Shutesbury | 73173 | NO | 2
Somerset | 72558 | NO | 5
Somerville | 66866 | YES | 4
South Hadley | 62803 | YES | 2
Southampton | 68693 | NO | 2
Southborough | 149375 | NO | 3
Southbridge | 42376 | YES | 3
Southwick | 81967 | NO | 2
Spencer | 60943 | YES | 3
Springfield | 34731 | YES | 2
Sterling | 90455 | NO | 3
Stockbridge | 57981 | YES | 1
Stoneham | 76218 | NO | 4
Stoughton | 74688 | NO | 5
Stow | 131500 | NO | 3
Sturbridge | 79711 | NO | 3
Sudbury | 169505 | NO | 3
Sunderland | 50417 | YES | 2
Sutton | 111804 | NO | 3
Swampscott | 96494 | NO | 4
Swansea | 77345 | NO | 5
Taunton | 52225 | YES | 5
Templeton | 68929 | NO | 2
Tewksbury | 87496 | NO | 4
Tisbury | 42727 | YES | 5
Tolland | 85750 | NO | 1
Topsfield | 121157 | NO | 4
Townsend | 82674 | NO | 3
Truro | 58060 | YES | 5
Tyngsborough | 93108 | NO | 4
Tyringham | 77750 | NO | 1
Upton | 111979 | NO | 3
Uxbridge | 86768 | NO | 3
Wakefield | 85156 | NO | 4
Wales | 52500 | YES | 2
Walpole | 90332 | NO | 5
Waltham | 73162 | NO | 4
Ware | 49630 | YES | 2
Wareham | 62560 | YES | 5
Warren | 42538 | YES | 2
Warwick | 54911 | YES | 2
Washington | 69583 | NO | 1
Watertown | 86461 | NO | 6
Wayland | 142306 | NO | 3
Webster | 48650 | YES | 3
Wellesley | 159615 | NO | 6
Wellfleet | 45746 | YES | 5
Wendell | 38636 | YES | 2
Wenham | 116875 | NO | 4
West Boylston | 73365 | NO | 3
West Bridgewater | 81573 | NO | 5
West Brookfield | 57381 | YES | 2
West Newbury | 122969 | NO | 4
West Springfield | 52806 | YES | 2
West Stockbridge | 65455 | YES | 1
West Tisbury | 73843 | NO | 5
Westborough | 100552 | NO | 3
Westfield | 60845 | YES | 2
Westford | 125143 | NO | 3
Westhampton | 79583 | NO | 2
Westminster | 87273 | NO | 3
Weston | 201200 | NO | 6
Westport | 80840 | NO | 5
Westwood | 128813 | NO | 6
Weymouth | 69099 | NO | 6
Whately | 75982 | NO | 2
Whitman | 76494 | NO | 5
Wilbraham | 87303 | NO | 2
Williamsburg | 65147 | YES | 1
Williamstown | 73397 | NO | 1
Wilmington | 100536 | NO | 4
Winchendon | 59332 | YES | 2
Winchester | 141829 | NO | 4
Windsor | 71731 | NO | 1
Winthrop | 64169 | YES | 6
Woburn | 77883 | NO | 4
Worcester | 46105 | YES | 3
Worthington | 71300 | NO | 1
Wrentham | 99302 | NO | 5
Yarmouth | 55858 | YES | 5